## Risk_Assessement
Description	Evaluation	Probability	Impact level	Responsibility	Response	Control Measures

Website Code does not work	The code is broken or some parts works only	Medium	High	Coder - Attila	Revert to most recent stable version	Tests always have to be carried out
Website Code test does not work	The code test is not ready or not working	High	Medium	Coder - Attila	Has to be fixed or finalized asap	Writing the test immediately after the code
Problems with Mysql tables	Tables do not work or do not reflect customers needs	Low	High	Coder - Attila	Checking on the code asap	Need accurate details of the customer's need
Virtual machine goes down	Application goes offline	Low	High	DevOps - Attila	Checking on the vm and contacting service provider	Having back up machines ready
Website design is not adequate	Website design does not reflect client's need	Medium	Low	Project Manager	Talking to the client, reevaluate ideas	Need accurate details of the customer's need
Cyber security is not adequete	Some parts of the code or the website is exposed	Low	Low	Coder - Attila	White hacking test	Cybersecurity plan has to be done
Deadlines are not met	Not meeting the deadlines	Medium	Medium	DevOps - Attila	Assigning new deadlines syncronised with plan	Deadlines has to be clear and realistic